## Introduction
GateIn Sniff test / Total time: 60mins

	Product Version
	Revision (svn)
	Date

	Testers	Environment		NotRun	Test not yet run
	hang.nguyen	FF		Passed	Test is ok
				Blocked	Could not run the test (another bug is blocking)
				Failed	Test failed, a bug is entered on it (please add the bug ID)
				N/A	Test is not possible to run on this version

	Test Result
	Failed	1
	OK	28

## GateIn_SniffTests
Category	Group function	ID	Checks list	Description	Expected Result	Test Result	JIRA Issue	Comments	Priority	Tester
Public mode	W3C	SNF_PRL_01	WC3 check for pages in public	- validate HTML code	Have some error	Failed	http://jira.exoplatform.org/browse/PORTAL-3555		Minor	hangnguyen
Public mode	Register	SNF_PRL_02	Create new account	Create new Account	New account is created successfully with valid input values	OK			Major	hangnguyen
Public mode	Language	SNF_PRL_03	Change displaying language	- Change Language / - Check result of change	Portal in public mode is displayed in new selected language	OK			Minor	hangnguyen
Public mode	Sign In/Out	SNF_PRL_04	Sign in/out	- Sign in / - Sign out	Show portal in private/public mode after sign in/out	OK			Minor	hangnguyen
Public mode	Remember my login	SNF_PRL_05			Save user/password of user	OK
Private mode	Organization portlet	SNF_PRL_06	Users Management	List/edit/delete user	- Users list is shown properly / - Edit/Delete user successfully	OK			Major	hangnguyen
Private mode	Organization portlet	SNF_PRL_07	Groups Management	- Create/delete Group / - Add user into group	- Groups tree is shown properly / - Add/Edit/Delete group, add user into group successfully	OK			Major	hangnguyen
Private mode	Organization portlet	SNF_PRL_08	Memberships Management	Create/delete membership	Add/Edit/Delete membership type successfully	Failed		delete membership is manager → unknown error	Minor	hangnguyen
Private mode	Portlet Registry portlet	SNF_PRL_09	Import portlet	Click Auto import	All existing portlets are imported successfully	OK			Major	hangnguyen
Private mode	Portlet Registry portlet	SNF_PRL_10	Create/Delete category	Create/Delete category with simple cases	Create/Delete category successfully	OK			Minor	hangnguyen
Private mode	Portlet Registry portlet	SNF_PRL_11	Add application into category	Add application into category	Applications can be added into existing category	OK		Lose resource-bundle of UIAddApplicationForm	Minor	hangnguyen
Private mode	Portlet Registry portlet	SNF_PRL_12	Add gadget(remote/create new)	Add gadget(remote/create new)	No error when add new gadget with simple case	OK			Minor	hangnguyen
Private mode	I18n portlet	SNF_PRL_13	Create new resource	Create new resource	Create resource is done with valid values in simple case	Failed	http://jira.exoplatform.org/browse/PORTAL-3559	NPE	Minor	hangnguyen
Private mode	Sitemap portlet	SNF_PRL_14	Link to pages	Click on link to move to another page	Show the selected page	OK			Minor	hangnguyen
Private mode	Portal Navigation	SNF_PRL_15	Create new portal	Create new portal in simple case	New portal is created successfully	OK		Now, new portal don't update in list, must be click refresh	Major	hangnguyen
Private mode	Portal Navigation	SNF_PRL_16	Edit portal	Make change for current using portal	Changes somethings ( layout/navigation/Nav's properties) successfully	OK			Major	hangnguyen
Private mode	Portal Navigation	SNF_PRL_17	Delete portal	Delete a portal from list	Deleted portal disappears from existing portals list	OK			Minor	hangnguyen
Private mode	Portal Navigation	SNF_PRL_18	Change using portal	- Create new portal / - Select new added to portal to use	Current using portal is changed by new selected	OK			Major	hangnguyen
Private mode	Site editor	SNF_PRL_19	- Create/Edit page/Edit site layout for portal	- Create/Edit pages in Site Editor in simple case / - Edit site layout in Site Editor in simple case	- Create/Edit page/Edit site layout for portal successfully	OK			Major	hangnguyen
Private mode	Group Navigation	SNF_PRL_20	Add Navigation	Add Navigation in simple case	Add Navigation successfully	OK		Occur bug when root select page other user	Minor	hangnguyen
Private mode	Group Navigation	SNF_PRL_21	- Edit navigation/Edit properties/Delete/ in Group Navigation	- Create new node / - Edit added / - Delete existing node	Actions are done	OK			Major	hangnguyen
Private mode	Group Navigation	SNF_PRL_22	Edit page of node	Make change for a node's page	Save changes successfully	OK			Minor	hangnguyen
Private mode	Group Navigation	SNF_PRL_23	Move up/down a node	- Select 1 node / - Do moving up/down	Actions are done	Failed	http://jira.exoplatform.org/browse/PORTAL-3558	Root can't edit page for other user	Major	hangnguyen
Private mode	Site editor	SNF_PRL_24	- Create/Edit page/Edit site layout for group	- Create/Edit pages in Site Editor in simple case / - Edit site layout in Site Editor in simple case	- Create/Edit page/Edit site layout for group successfully	OK			Major	hangnguyen
Private mode	Dashboard	SNF_PRL_25	Add/drag-drop	- Add/drag-drop Gadget	Gadget is added/dragged_dropped successfully	Failed		when maxi or mini gadget will be lost	Major	hangnguyen
Private mode	Dashboard editor	SNF_PRL_26	- Create/Edit page/Edit site layout for user	- Create/Edit pages in Site Editor in simple case / - Edit site layout in Site Editor in simple case	- Create/Edit page/Edit site layout for user successfully	Failed	http://jira.exoplatform.org/browse/PORTAL-3552	Can't edit dashboard portlet	Major	hangnguyen
Private mode	Language	SNF_PRL_27	Change language	- Change displaying language	Portal in private mode is displayed in new selected language	OK			Minor	hangnguyen
Private mode	Skin	SNF_PRL_28	Change skin	- Change displaying skin	Portal in private mode is displayed in new selected skin	OK			Minor	hangnguyen
Private mode	Personal account settings	SNF_PRL_29	Setting account	Change user profile + password	Save changes successfully	OK			Minor	hangnguyen
Private mode	Logo portlet	SNF_PRL_30	change logo	Change logo for portal	Show logo successfully	Failed		Display error	Minor	hangnguyen