## Cover
AIO REGRESSION TEST CASES
Version:	1.3
Issue date:	24/12/2010
Project Suite:
Project Name:	GateIn
Total Cases:	29
Test Status:	Passed: Test is OK / Blocked: Could not run the test (another bug is blocking) / Failed: Test failed, a bug is entered on it (please add the bug ID) / N/A: Test is not possible to run on this version

Record of change:
Effective Date	Version	Change description	Originator	Reviewer/ / Approver	Reference
04/Oct/10	1.0	AIO split to products	minh.nguyen
	1.1	Missing: (technique) / - Portal-3755 / - Portal- 3814 / - Portal-3806 / - Portal-3780 / PORTAL-3772 / PORTAL-3444 / PORTAL-3743	minh.nguyen
2/Nov/10	1.2	Portal-2983 / Portal-3827 / Portal-3823 / Portal-3836 / Portal-3841 / Portal-3857	minh.nguyen
24/Dec/10	1.3	Update with new format	hang.nguyen

## Check_List
Check List / Based on Product built version:		BugID	Priority
Id	Main cases	Priority	Priority
Bugs on version 1.6.1
REG_GTN_CCP_120	Change site to current - navigation is changing, page is not	Portal-3435	High
REG_GTN_CCP_122	No possible accented characters in the user profile	Portal-3689	Low
Bugs on version 1.6.5
REG_GTN_CCP_314	Several JS problems with IE 7	ALL-297, WCM-2713, PORTAL-3766	High
REG_GTN_CCP_51	Check when click twice on Sign In button	PORTAL-3221, WCM-2504	Low
REG_GTN_CCP_366	Title of button close window in popup not available in french	ALL-325, PORTAL-3773	Low
REG_GTN_CCP_394	Check if mandatory textarea (*) on the right , not in the bottom	Portal-3739	High
Bugs on version 1.6.6
REG_GTN_CCP_372	Check showing popup save-success after saving CLV portlet	Portal-3776	High
REG_GTN_CCP_391	Check adding portlet by drag/drop while editing page	Portal-3787	High
REG_GTN_CCP_395	Check moving portlet inside a page while editing page by wizard	Portal-3789	High
REG_GTN_CCP_461	Check showing user page for anonymous user	Portal-3816	High
REG_GTN_PRL_001	Check Login when URL contain plus ('+') symbol	Portal-3684	Low
REG_GTN_CCP_379	Check deleting Portlet Preference in System files when abort adding new page after saving portlet preference	Portal-3790	Low
REG_GTN_CCP_428	Check applying changes the internationalization of navigation	Portal-3808	High
REG_GTN_CCP_464	Check hitting enter key to do search user	Portal-3817	Low
REG_GTN_CCP_466	Check searching user with apostrophes in First/Last name	Portal-3818	High
REG_GTN_PRL_002	Check if tooltip on Application Registry are translated into French	Portal-3840	Low
REG_GTN_PRL_003	Check Login in French	Portal-3812	Low
Bugs on version 1.6.7
REG_GTN_PRL_004	Check changing size of container in page	Portal-2983	High
REG_GTN_PRL_005	Check when drag & drop 1 row container into page	Portal-3827	Low
REG_GTN_PRL_006	Check when drag & drop 1 column container into page	Portal-3827	Low
REG_GTN_PRL_007	Check when drag & drop 1 row container into site	Portal-3827	Low
REG_GTN_PRL_008	Check when drag & drop 1 column container into site	Portal-3827	Low
REG_GTN_CCP_499	Check when drag & drop portlet in IE7	Portal-3823	High
REG_GTN_PRL_006	Check French label in Login form	Portal-3836	Low
REG_GTN_PRL_007	Check value of description when edit membership type	Portal-3841	Low
REG_GTN_CCP_584	Check show page after edit navigation	Portal-3857	Low

## Bugs_v1_6_1
	TEST CASES					Passed	0
				Failed	0
	Function List:	Bugs on Portal 2.5.x for regression test					Blocked	0
	Total Main Cases:	2					Untested	0
				N/A	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description
001	REG_GTN_CCP_120	001	Portal/REG_GTN_CCP_120	Change site to current - navigation is changing, page is not	Step 1: Import application	- Login by admin / - Go to Group/Application Registry / - Click on Auto Import link	All applications are imported	High	Portal-3435	after step 4: Now navigation is changed to Home (I assume that is first permitted navigation) what is OK, but visible page is still the sitemap one. It's a bug.
	REG_GTN_CCP_120	001	Portal/REG_GTN_CCP_120	Change site to current - navigation is changing, page is not	Step 2: Create sitemap page	- Go to Site Editor/Add page wizard / - Input needed values / - At step 3: drag & drop Sitemap portlet into page / - Save	Create new page successfully	High	Portal-3435
	REG_GTN_CCP_120	001	Portal/REG_GTN_CCP_120	Change site to current - navigation is changing, page is not	Step 3: View sitemap page	- Select to view sitemap page	The sitemap page is displayed lists all pages on current portal	High	Portal-3435
	REG_GTN_CCP_120	001	Portal/REG_GTN_CCP_120	Change site to current - navigation is changing, page is not	Step 4: Change site to current	erase part of an url and submit http://domain/portal/public/classic	Now navigation is changed to Home. Visible page is Home also	High	Portal-3435
002	REG_GTN_CCP_122	001	Portal/REG_GTN_CCP_122	No possible accented characters in the user profile	Step 1: Create user with accent	- Click Register / - Input valid value in fields (contain accent in FirstName or LastName) / - Click Save	New user is added successfully	Low	Portal-3689
	REG_GTN_CCP_122	001	Portal/REG_GTN_CCP_122	No possible accented characters in the user profile	Step 2: Check when update user info with accents	- Go to Community Management / - Click Edit icon at any user / - Change current FirstName/LastName with accent / - Click Save	Change is saved	Low	Portal-3689

## Bugs_v1_6_5
	TEST CASES					Passed	0
				Failed	0
	Function List:	Bugs on Portal 2.5.x for regression test					Blocked	0
	Total Main Cases:	6					Untested	0
				N/A	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description
001	REG_GTN_CCP_314	001	Portal/REG_GTN_CCP_314	Several JS problems with IE 7	Step 1: Open form to edit portal layout	- Login with root / - Open the edit portal layout page	Edit portal layout form is shown	High	ALL-297, WCM-2713, PORTAL-3766	the drag and drop is not accurate, we have to drag the portlet far from where it will actually be dropped
	REG_GTN_CCP_314	001	Portal/REG_GTN_CCP_314	Several JS problems with IE 7	Step 2: Drag & drop container	- Drag & drop a column container into page	Drag & drop successfully	High	ALL-297, WCM-2713, PORTAL-3766
	REG_GTN_CCP_314	001	Portal/REG_GTN_CCP_314	Several JS problems with IE 7	Step 3: Add portlet into page	Add many portlets in the columns, next to each other	The drag and drop is well done	High	ALL-297, WCM-2713, PORTAL-3766
002	REG_GTN_CCP_51	001	Portal/REG_GTN_CCP_51	Check when click twice on Sign In button	Step 1: Sign in	- Try to access /private/* / - Input valid username & password / Enter login and hit the button twice	Login successfully with no error	Low	PORTAL-3221, WCM-2504	Login Page: HTTP 404, when clickin twice on "Connection Button"
003	REG_GTN_CCP_366	001	Portal/REG_GTN_CCP_366	Title of button close window in popup not available in french	Step 1: Open any popup	- Change display language to French / - Open any pop up then move the mouse to the cross icon at the top right of the popup	The tool tip (title) is well displayed in French	Low	ALL-325, PORTAL-3773
004	REG_GTN_CCP_394	001	Portal/REG_GTN_CCP_394	Check if mandatory textarea (*) on the right , not in the bottom	Step 1: Show form to check madatory field	- Go to Site Explorer --> Choose any drive / - Click Add document / - Select any template & check the mandator icon (*) of textarea	The mandatory icon must be on the right	High	Portal-3739	The mandatory icon sometimes at the bottom
005	REG_GTN_CCP_394	001	Portal/REG_GTN_CCP_394	Check if the max length of Group label is up to 50 characters	Step 1: Show add new group form	- Login by admin / - Go to Group → Community Management / - Choose Group Management tab / - Click + icon in group tree from left pane	Add new group icon is shown	Low	Portal-3740	Max length of Group label is limited to 30 characters
	REG_GTN_CCP_394	001	Portal/REG_GTN_CCP_394	Check if the max length of Group label is up to 50 characters	Step 2: Check max length of Group label field	- Input valid Name / - Input less than 3 or over 50 characters into Label / - Click Save	Show message alerts the group label must have from 3 to 50 characters	Low	Portal-3740
006	REG_GTN_CCP_394	002	Portal/REG_GTN_CCP_394	Check the translation of label in message popup	Step 1: Change language	Go to Language Setting & select 1 language to display	The site is displayed in selected language	Low	Portal-3658	The message labels ("Error", "Warning" and "Info") cannot be localized
	REG_GTN_CCP_394	002	Portal/REG_GTN_CCP_394	Check the translation of label in message popup	Step 2: Show message popup	- Do action that will show a message popup (e.g: Create new group with invalid value)	Message popup is shown with labels are well translated in selected language	Low	Portal-3658

## Bugs_v1_6_6
	TEST CASES					Passed	0
				Failed	0
	Function List:	Bugs on Portal 2.5.x for regression test					Blocked	0
	Total Main Cases:	12					Untested	0
				N/A	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description
001	REG_GTN_CCP_372	001	Portal/REG_GTN_CCP_372	Check showing popup save-success after saving CLV portlet	Step 1: Go to ACME site	- Login by root / - Select acme site	acme site is shown, focus on Home page	High	Portal-3776
	REG_GTN_CCP_372	001	Portal/REG_GTN_CCP_372	Check showing popup save-success after saving CLV portlet	Step 2: Switch to edit mode	Click icon at the top right corner to switch to Edit mode	Edit mode is selected, there's quick edit icon for each portlet in page	High	Portal-3776
	REG_GTN_CCP_372	001	Portal/REG_GTN_CCP_372	Check showing popup save-success after saving CLV portlet	Step 3: Show form to edit a CLV	Click Quick edit icon at a CLV (e.g: Company News)	Content List Viewer Configuration form is shown	High	Portal-3776
	REG_GTN_CCP_372	001	Portal/REG_GTN_CCP_372	Check showing popup save-success after saving CLV portlet	Step 4: Show form to select content	- Choose Manual mode / - Click icon at the row below to select content	Multiple Content selector panel is show	High	Portal-3776
	REG_GTN_CCP_372	001	Portal/REG_GTN_CCP_372	Check showing popup save-success after saving CLV portlet	Step 5: Select content to be viewed	- Select path from left pane then choose content from right pane / - Click Save	Selected content(s) is listed in Content List viewer configuration	High	Portal-3776
	REG_GTN_CCP_372	001	Portal/REG_GTN_CCP_372	Check showing popup save-success after saving CLV portlet	Step 6: Complete editing CLV	Click Save in Content List viewer configuration	Content List viewer configuration form is closed, a message is shown to alert configure successfully	High	Portal-3776	Close the edit mode. Saving succes message's popup appears not in its normal place.
002	REG_GTN_CCP_391	001	Portal/REG_GTN_CCP_391	Check adding portlet by drag/drop while editing page	Step 1: Go to ACME site	- Login by root / - Select acme site	acme site is shown, focus on Home page	High	Portal-3787
	REG_GTN_CCP_391	001	Portal/REG_GTN_CCP_391	Check adding portlet by drag/drop while editing page	Step 2: Show form to edit page by wizard	- Select Site Editor-> Edit Page Wizard from admin bar	Edit current page by wizard is show, stay at step 2	High	Portal-3787
	REG_GTN_CCP_391	001	Portal/REG_GTN_CCP_391	Check adding portlet by drag/drop while editing page	Step 3: Move to step 3 to change portlet	- Click Next to move to step 3	Step 3 of edit page wizard form is show	High	Portal-3787
	REG_GTN_CCP_391	001	Portal/REG_GTN_CCP_391	Check adding portlet by drag/drop while editing page	Step 4: Add container into page	- Drag & drop a mixed container into the page	Mixed container is added into page	High	Portal-3787
	REG_GTN_CCP_391	001	Portal/REG_GTN_CCP_391	Check adding portlet by drag/drop while editing page	Step 5: Add portlet into new added container	Drag & drop portlet into page	Drag & drop action is well done. The portlet is added into page	High	Portal-3787	portlet freeze in the middle of the page / From it, we can drag portlets as if we did the operation from the left side.
003	REG_GTN_CCP_395	001	Portal/REG_GTN_CCP_395	Check moving portlet inside a page while editing page by wizard	Step 1: Go to ACME site	- Login by root / - Select acme site	acme site is shown, focus on Home page	High	Portal-3789
	REG_GTN_CCP_395	001	Portal/REG_GTN_CCP_395	Check moving portlet inside a page while editing page by wizard	Step 2: Show form to edit page by wizard	- Select Site Editor-> Edit Page Wizard from admin bar	Edit current page by wizard is show, stay at step 2	High	Portal-3789
	REG_GTN_CCP_395	001	Portal/REG_GTN_CCP_395	Check moving portlet inside a page while editing page by wizard	Step 3: Move to step 3 to change portlet	- Click Next to move to step 3	Step 3 of edit page wizard form is show	High	Portal-3789
	REG_GTN_CCP_395	001	Portal/REG_GTN_CCP_395	Check moving portlet inside a page while editing page by wizard	Step 4: Add container into page	Drag & drop a column container into page	Column container is added into page	High	Portal-3789
	REG_GTN_CCP_395	001	Portal/REG_GTN_CCP_395	Check moving portlet inside a page while editing page by wizard	Step 5: Change portlet position inside page	Change portlets' positions in the container by drag & drop	Drag & drop action is well done. The portlet is moved to new place	High	Portal-3789	Changing portlet's position affects the others as if they are concerned by the drag and drop operation
004	REG_GTN_CCP_461	001	Portal/REG_GTN_CCP_461	Check showing user page for anonymous user	Step 1: Create user page	- Login classic site by root / - Go to Site Administrator/Manage Pages / - Create new page for user	- Create page successfully / - Permission for this page is blank (default is set for page owner only)	High	Portal-3816
	REG_GTN_CCP_461	001	Portal/REG_GTN_CCP_461	Check showing user page for anonymous user	Step 2: Add node on classic portal link to user's page	- Go to Site Editor/Edit Navigation / - Select classic site navigation / - Add new node & select to added page of user at step 1 / - Click Save & Finish to complete	New node link to user page is added successfully on classic portal navigation	High	Portal-3816
	REG_GTN_CCP_461	001	Portal/REG_GTN_CCP_461	Check showing user page for anonymous user	Step 3: Check if anonymous user can see private page	- Logout	- Classic site is displayed in public mode / - The node added at step 2 is not displayed in navigation for anonymous user	High	Portal-3816	java.lang.NullPointerException in UserACL for ANONYMOUS users
005	REG_GTN_PRL_001	001	Portal/REG_GTN_PRL_001	Check Login when URL contain plus ('+') symbol	Step 1: Check jump to page by input URL directly	- Login as root / - Type this URL : http://localhost:8080/portal/private/classic/organization/newStaff/	Page is displayed	Low	Portal-3684
	REG_GTN_PRL_001	001	Portal/REG_GTN_PRL_001	Check Login when URL contain plus ('+') symbol	Step 2: Check jump to page by input URL directly	Now type this URL : http://localhost:8080/portal/private/classic/organization/newStaff/xxxxx	Page is displayed	Low	Portal-3684
	REG_GTN_PRL_001	001	Portal/REG_GTN_PRL_001	Check Login when URL contain plus ('+') symbol	Step 3: Check jump to page by input URL directly	Now, type this URL : http://localhost:8080/portal/private/classic/organization/newStaff/xxx+xxxx	Page is displayed	Low	Portal-3684	Plus ('+') symbol in an URL causes an ERROR 500 and exception in console
006	REG_GTN_CCP_379	001	Portal/REG_GTN_CCP_379	Check deleting Portlet Preference in System files when abort adding new page after saving portlet preference	Step 1: Show Add new page form	- Login by admin / (- Go to Groups/Application Registry & do Auto Import portlet if this action has not been done yet) / - Go to Site Editor/Add page wizard	Add new page by wizard is show	Low	Portal-3790
	REG_GTN_CCP_379	001	Portal/REG_GTN_CCP_379	Check deleting Portlet Preference in System files when abort adding new page after saving portlet preference	Step 2: Add portlet into page	- Input Page name / - At step 3: add a portlet window associatied with a preference by drag & drop into page (e.g: IFRAME portlet)	Drag & drop action is well done. The portlet is added into page	Low	Portal-3790
	REG_GTN_CCP_379	001	Portal/REG_GTN_CCP_379	Check deleting Portlet Preference in System files when abort adding new page after saving portlet preference	Step 3: Edit portlet	- Click icon to edit added portlet / - In edit form: Click Save to save the URL / - Click Close	Edit portlet form is closed	Low	Portal-3790
	REG_GTN_CCP_379	001	Portal/REG_GTN_CCP_379	Check deleting Portlet Preference in System files when abort adding new page after saving portlet preference	Step 4: Abort adding new page after saved portlet preference	Click Abort to escape adding new page	No new page is added	Low	Portal-3790
	REG_GTN_CCP_379	001	Portal/REG_GTN_CCP_379	Check deleting Portlet Preference in System files when abort adding new page after saving portlet preference	Step 5: Check Portlet preference	- Go to Groups/Sites Explorer/System Files / - Select /exo:registry/exo:applications/MainPortalData/classic/portletPreferences	That Portlet's Portlet Preference is not there	Low	Portal-3790	That Portlet's Portlet Preference is still there
007	REG_GTN_CCP_379	002	Portal/REG_GTN_CCP_379	Check deleting Portlet Preference in System files when abort editing page after saving portlet preference	Step 1: Show edit page form	- Login by admin / (- Go to Groups/Application Registry & do Auto Import portlet if this action has not been done yet) / - Go to Site Editor/Edit page wizard	Edit page by wizard is show	Low	Portal-3790
	REG_GTN_CCP_379	002	Portal/REG_GTN_CCP_379	Check deleting Portlet Preference in System files when abort editing page after saving portlet preference	Step 2: Add portlet into page	- Input Page name / - At step 3: add a portlet window associatied with a preference by drag & drop into page (e.g: IFRAME portlet)	Drag & drop action is well done. The portlet is added into page	Low	Portal-3790
	REG_GTN_CCP_379	002	Portal/REG_GTN_CCP_379	Check deleting Portlet Preference in System files when abort editing page after saving portlet preference	Step 3: Edit portlet	- Click icon to edit added portlet / - In edit form: Click Save to save the URL / - Click Close	Edit portlet form is closed	Low	Portal-3790
	REG_GTN_CCP_379	002	Portal/REG_GTN_CCP_379	Check deleting Portlet Preference in System files when abort editing page after saving portlet preference	Step 4: Abort editing page after saved portlet preference	Click Abort to escape editing page	Page has no change	Low	Portal-3790
	REG_GTN_CCP_379	002	Portal/REG_GTN_CCP_379	Check deleting Portlet Preference in System files when abort editing page after saving portlet preference	Step 5: Check Portlet preference	- Go to Groups/Sites Explorer/System Files / - Select /exo:registry/exo:applications/MainPortalData/classic/portletPreferences	That Portlet's Portlet Preference is not there	Low	Portal-3790	That Portlet's Portlet Preference is still there
008	REG_GTN_CCP_428	001	Portal/REG_GTN_CCP_428	Check applying changes the internationalization of navigation	Step 1: Go to Internationalization page	- Login by admin / - Go to Groups/Internationalization	Internationalization page is shown	High	Portal-3808
	REG_GTN_CCP_428	001	Portal/REG_GTN_CCP_428	Check applying changes the internationalization of navigation	Step 2: View resource	- Search to find resource (e.g: locale.navigation.group.platform.administrators) / - Click icon to view at the line of current using language	Resource content is shown in view mode (can not change)	High	Portal-3808
	REG_GTN_CCP_428	001	Portal/REG_GTN_CCP_428	Check applying changes the internationalization of navigation	Step 3: Edit resource	- Click Edit / - Change value for administration.portalAdmin / - Save / - Select 1 page from admin bar to refresh browser / - Move mouse over Groups in Admin bar	“Administration” is changed to new edited value	High	Portal-3808	Internationalization of navigation is applied only when user logout/change language
009	REG_GTN_CCP_464	001	Portal/REG_GTN_CCP_464	Check hitting enter key to do search user	Step 1: Show User management form	- Login by admin / - Go to Groups/Community Management	Community Management is shown, User Management is displayed	Low	Portal-3817
	REG_GTN_CCP_464	001	Portal/REG_GTN_CCP_464	Check hitting enter key to do search user	Step 2: Search user	- Input value to search into text field / - Select search condition / - Hit enter key	Search result is returned	Low	Portal-3817	Page load, result does not change
010	REG_GTN_CCP_466	001	Portal/REG_GTN_CCP_466	Check searching user with apostrophes in First/Last name	Step 1: Add user	Register an user who has a Firstname or a lastname with apostrophes (EXP: L'test)	Register successfully	High	Portal-3818
	REG_GTN_CCP_466	001	Portal/REG_GTN_CCP_466	Check searching user with apostrophes in First/Last name	Step 2: Search user	- Login by admin / - Go to Community Management and search the user L'test by choosing the lastname or the firsname as a criterion of the search	New added user is returned in search result	High	Portal-3818	It is expected to have this user as a result but the following message is shown: "No result found"
011	REG_GTN_PRL_002	001	Portal/REG_GTN_PRL_002	Check if tooltip on Application Registry are translated into French	Step 1: Change language	- Login by admin / - Select Language Settings from admin bar / - Choose French / - Click Apply	Current site is translated into French	Low	Portal-3840
	REG_GTN_PRL_002	001	Portal/REG_GTN_PRL_002	Check if tooltip on Application Registry are translated into French	Step 2: Check Application Registry	- Go to Group → Application Registry	Tool tip on all labels are translated into French	Low	Portal-3840	some tool tips on Application Registry are not translated into French. / * Edit category / * Delete Category / * Add application into category / * Edit application / * Delete Application / * Delete gadget
012	REG_GTN_PRL_003	001	Portal/REG_GTN_PRL_003	Check Login in French	Step 1: Show Home page at public	- Input URL to show portal (e.g: http://localhost:8080/portal)	Go to classic portal in public mode	Low	Portal-3812
	REG_GTN_PRL_003	001	Portal/REG_GTN_PRL_003	Check Login in French	Step 2: Change language	- Click Change language link / - Choose French / - Click Apply	All labels are well translated	Low	Portal-3812
	REG_GTN_PRL_003	001	Portal/REG_GTN_PRL_003	Check Login in French	Step 3: Login	- Click Connexion / - Input Username + Password / - Click Connexion	Go to classic portal in private mode	Low	Portal-3812	When trying to login to AIO 1.6.5 with browser in French → throw exception

				d

				d

				d

## Bugs_v1_6_7
	TEST CASES					Passed	0
				Failed	0
	Function List:	Bugs on Portal 2.5.x for regression test					Blocked	0
	Total Main Cases:	9					Untested	0
				N/A	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description
001	REG_GTN_PRL_004	001	Portal/REG_GTN_PRL_004	Check changing size of container in page	Step 1: Show container list at step 3 of add page wizard	- Login by admin / - Click Sites Editor → Edit page wizard / - Input Name / - Click Next to move to step 2 then Next to move to step 3 / - Click Show Container icon	Containers list is shown on the left	High	Portal-2983
	REG_GTN_PRL_004	001	Portal/REG_GTN_PRL_004	Check changing size of container in page	Step 2: Switch to edit mode	- Select In columns / - Drag & drop 2 Column Container into page	Container is added into page with 2 columns 50%	High	Portal-2983
	REG_GTN_PRL_004	001	Portal/REG_GTN_PRL_004	Check changing size of container in page	Step 3: Edit container	- Click Edit icon at the first container & input 30% for Width then Save / - Click Edit icon at the second container & input 70% for Width then Save	There're 2 columns of 30/70	High	Portal-2983	the portlet is taking 30% of the first container, the second one 70% of the container. (and each container takes 50% of the page)
002	REG_GTN_PRL_005	001	Portal/REG_GTN_PRL_005	Check when drag & drop 1 row container into page	Step 1: Show edit page wizard	- Login by admin / - Select Edit page wizard under Sites Editor / - Click Next to move to step 3	Edit page wizard step 3 is shown	Low	Portal-3827
	REG_GTN_PRL_005	001	Portal/REG_GTN_PRL_005	Check when drag & drop 1 row container into page	Step 2: Show container control	Click Show container icon on the left	Container list is shown on the left	Low	Portal-3827
	REG_GTN_PRL_005	001	Portal/REG_GTN_PRL_005	Check when drag & drop 1 row container into page	Step 3: Add container into page	- Choose In Lines / - Drag & drop 1 row container into page	The container is added in page and well displayed	Low	Portal-3827
003	REG_GTN_PRL_005	002	Portal/REG_GTN_PRL_005	Check when drag & drop 1 column container into page	Step 1: Show edit page wizard	- Login by admin / - Select Edit page wizard under Sites Editor / - Click Next to move to step 3	Edit page wizard step 3 is shown	Low	Portal-3827
	REG_GTN_PRL_005	002	Portal/REG_GTN_PRL_005	Check when drag & drop 1 row container into page	Step 2: Show container control	Click Show container icon on the left	Container list is shown on the left	Low	Portal-3827
	REG_GTN_PRL_005	002	Portal/REG_GTN_PRL_005	Check when drag & drop 1 row container into page	Step 3: Add container into page	- Choose In Column / - Drag & drop 1 column container into page	The container is added in page and well displayed	Low	Portal-3827
004	REG_GTN_PRL_005	003	Portal/REG_GTN_PRL_005	Check when drag & drop 1 row container into site	Step 1: Show edit site form	- Login by admin / - Select Edit Site under Sites Editor	Edit current site form is shown	Low	Portal-3827
	REG_GTN_PRL_005	003	Portal/REG_GTN_PRL_005	Check when drag & drop 1 row container into site	Step 2: Show container control	Click Show container control icon on the left	Container list is shown on the left	Low	Portal-3827
	REG_GTN_PRL_005	003	Portal/REG_GTN_PRL_005	Check when drag & drop 1 row container into site	Step 3: Add container into page	- Choose In Lines / - Drag & drop 1 row container into site	The container is added in site and well displayed	Low	Portal-3827
005	REG_GTN_PRL_005	004	Portal/REG_GTN_PRL_005	Check when drag & drop 1 row container into site	Step 1: Show edit site form	- Login by admin / - Select Edit Site under Sites Editor	Edit current site form is shown	Low	Portal-3827
	REG_GTN_PRL_005	004	Portal/REG_GTN_PRL_005	Check when drag & drop 1 row container into site	Step 2: Show container control	Click Show container control icon on the left	Container list is shown on the left	Low	Portal-3827
	REG_GTN_PRL_005	004	Portal/REG_GTN_PRL_005	Check when drag & drop 1 row container into site	Step 3: Add container into page	- Choose In Columns / - Drag & drop 1 column container into site	The container is added in site and well displayed	Low	Portal-3827
006	REG_GTN_CCP_499	001	Portal/REG_GTN_CCP_499	Check when drag & drop portlet in IE7	Step 1: Show edit site form	- Login acme by admin in IE7 / - Select Edit Site under Sites Editor	Edit current site form is shown	High	Portal-3823
	REG_GTN_CCP_499	001	Portal/REG_GTN_CCP_499	Check when drag & drop portlet in IE7	Step 2: Drag & drop portlet	Drag & drop 1 portlet to the right	The drag & drop action is well done	High	Portal-3823	It is dropped whenever the screen boarder are exceeded(not where the user needs it).
007	REG_GTN_PRL_006	001	Portal/REG_GTN_PRL_006	Check French label in Login form	Step 1: Show site in public	Input URL, e.g: http://localhost:8080/portal/public/classic/	Show classic site in public mode	Low	Portal-3836
	REG_GTN_PRL_006	001	Portal/REG_GTN_PRL_006	Check French label in Login form	Step 2: Change language	- Click Change Language link / - Choose French / - Click Apply	Site is displayed in French	Low	Portal-3836
	REG_GTN_PRL_006	001	Portal/REG_GTN_PRL_006	Check French label in Login form	Step 3: Show sign in form	Click Connexion link	Sign in form is shown with correct labels / Sign in=Connexion / User name=Utilisateur / Password=Mot de passe	Low	Portal-3836	When login in private modes, "Mot de" is displayed instead of "Mot de passe"
008	REG_GTN_PRL_007	001	Portal/REG_GTN_PRL_007	Check value of description when edit membership type	Step 1: Add new membership type	- Login as admin / - Go to Community Management / - Choose Membership Management / - Add new membership type with no description	New membership type is added	Low	Portal-3841
	REG_GTN_PRL_007	001	Portal/REG_GTN_PRL_007	Check value of description when edit membership type	Step 2: Edit membership type	Click edit icon at 1 existing membership (that has description)	Information of selected membership is shown in form below	Low	Portal-3841
	REG_GTN_PRL_007	001	Portal/REG_GTN_PRL_007	Check value of description when edit membership type	Step 3: Edit membership type	Click edit icon at new added membership type at step 1	Information of selected membership is shown in form below with blank description	Low	Portal-3841	Still show description of membership which selected before
009	REG_GTN_CCP_584	001	Portal/REG_GTN_CCP_584	Check show page after edit navigation	Step 1: Show edit navigation form	- Connect as root on the acme site / - Click on "Edit navigation" under Site Editor	Edit navigation form is shown	Low	Portal-3857
	REG_GTN_CCP_584	001	Portal/REG_GTN_CCP_584	Check show page after edit navigation	Step 2: Move node down	- Right-click on the node "Newsletter", then click Move Down / - Save and finish / - Click on the link "Newsletter" in the menu	The page of Newsletter appears well	Low	Portal-3857
	REG_GTN_CCP_584	001	Portal/REG_GTN_CCP_584	Check show page after edit navigation	Step 3: Show edit navigation form	- Click on "Edit navigation" under Site Editor (without returning to the home page)	Edit navigation form is shown	Low	Portal-3857
	REG_GTN_CCP_584	001	Portal/REG_GTN_CCP_584	Check show page after edit navigation	Step 4: Move node up	- Right-click on the node "Newsletter", then click Move Up / - Save and finish / - Click on the link "Newsletter" in the menu	The page of Newsletter appears well	Low	Portal-3857	The page of Newsletter isn't displayed, it remains on the home page

## Summary_Report
Portal Regression Tests List In AIO					Total cases

Id	Product	Functionality	Bug summary	Product bugID
REG_GTN_CCP_120	Portal	Portal	Change site to current - navigation is changing, page is not	Portal-3435	1	1.6.1
REG_GTN_CCP_122	Portal	Portal	No possible accented characters in the user profile	Portal-3689	1
REG_GTN_CCP_51	Portal	Portal	Login Page: HTTP 404, when clickin twice on "Connection Button"	PORTAL-3221	1	1.6.5
REG_GTN_CCP_314	Portal	Portal	Several JS problems with IE 7	WCM-2713 / PORTAL-3766	1
REG_GTN_CCP_366	Portal	Portal	Title of button close window in popup not available in french	PORTAL-3773	1
REG_GTN_CCP_394	Portal	Portal	Secours Catholique : Portal tickets backport / - Mandatory textarea (*) should be on the right , not in the bottom / - Checkoi inh if the max length of Group label is up to 50 characters / - Check the translation of label in message popup	PORTAL-3739 / PORTAL-3740 / Portal-3658	3
REG_GTN_CCP_372	Portal	Portal	Problem with popup save-success after saving portlet CLV	Portal-3776	1	1.6.6
REG_GTN_CCP_391	Portal	Portal	Problem in drag and drop when editing page	Portal-3787	1
REG_GTN_CCP_395	Portal	Portal	Problem in moving portlets when editing page	Portal-3789	1
REG_GTN_CCP_461	Portal	Portal	java.lang.NullPointerException in UserACL for ANONYMOUS users	Portal-3816	1
REG_GTN_PRL_001	Portal	Portal	Plus ('+') symbol in an URL causes an ERROR 500 and exception in console	Portal-3684	1
REG_GTN_CCP_379	Portal	Portal	Do not delete Portlet Preference in System Files when deleting portlets	Portal-3790	2
REG_GTN_CCP_428	Portal	Portal	Internationalization of navigation is applied only when user logout/change language	Portal-3808	1
REG_GTN_CCP_464	Portal	Portal	Find user: Enter key press not catch	Portal-3817	1
REG_GTN_CCP_466	Portal	Portal	Search of user with apostrophes	Portal-3818	1
REG_GTN_PRL_002	Portal	Portal	Some tooltip on Application Registry are not translated into French	Portal-3840	1
REG_GTN_PRL_003	Portal	Portal	Can't login, login page doesn't appear	Portal-3812	1
REG_GTN_PRL_004	Portal	Portal	Check changing size of container in page	Portal-2983	1	1.6.7
REG_GTN_PRL_005	Portal	Portal	Position of dragged object (One row container, One column container) is not under mouse in Edit page, Edit portal	Portal-3827	4
REG_GTN_CCP_499	Portal	Portal	Portlet is dropped automatically when exceeds screen border (using IE7)	Portal-3823	1
REG_GTN_PRL_006	Portal	Portal	Bug in Sign in form in French	Portal-3836	1
REG_GTN_PRL_007	Portal	Portal	Always take the value of description of next position when edit membership	Portal-3841	1
REG_GTN_CCP_584	Portal	Portal	Check show page after edit navigation	Portal-3857	1
Total					29